## Sheet1
WBS | Name | Start | Duration | Effort | Assigned Resources | % Done | Predecessors | Successors | Scheduling Mode | Calendar | Constraint Type | Constraint Date
1 | Launch SaaS Product | 2019-01-14 00:00 | 47 days | 4000 hours |  | 34% |  |  | Normal | General
1.1 | Setup web server | 2019-01-14 00:00 | 7 days | 576 hours |  | 42% |  |  | Normal | General
1.1.1 | Install Apache | 2019-01-14 00:00 | 3 days | 72 hours | Celia 100% | 50% |  | 15+2d | Normal | General
1.1.2 | Configure firewall | 2019-01-14 00:00 | 3 days | 144 hours | Celia 100%,Gloria 100% | 50% |  | 15 | Normal | General
1.1.3 | Setup load balancer | 2019-01-14 00:00 | 3 days | 264 hours | Lee 100%,Macy 100%,Dave 100%,Dan 100%,George 100% | 50% |  | 15 | Normal | General
1.1.4 | Configure ports | 2019-01-14 00:00 | 2 days | 48 hours |  | 50% |  | 15 | Normal | General
1.1.5 | Run tests | 2019-01-21 00:00 | 2 days | 48 hours |  | 0% | 11+2d;12;13;14 | 21 | Normal | General
1.2 | Website Design | 2019-01-23 00:00 | 15 days | 400 hours |  | 34% |  |  | Normal | General
1.2.1 | Contact designers | 2019-01-23 00:00 | 5 days | 160 hours | Rob 100%,Gloria 100% | 70% | 15 | 22 | Normal | General
1.2.2 | Create shortlist of three designers | 2019-01-30 00:00 | 1 day | 24 hours | George 100% | 60% | 21 | 23 | Normal | General
1.2.3 | Select & review final design | 2019-01-31 00:00 | 2 days | 48 hours |  | 50% | 22 | 24 | Normal | General
1.2.4 | Inform management about decision | 2019-02-02 00:00 | 0 days | 0 hours |  | 100% | 23 | 25 | Normal | General
1.2.5 | Apply design to web site | 2019-02-04 00:00 | 7 days | 168 hours | Macy 100% | 0% | 24 |  | Normal | General
1.3 | Setup Test Strategy | 2019-01-14 00:00 | 15 days | 744 hours |  | 15% |  | 4 | Normal | General
1.3.1 | Hire QA staff | 2019-01-14 00:00 | 5 days | 120 hours |  | 40% |  | 33 | Normal | General
1.3.2 | Write test specs | 2019-01-21 00:00 | 10 days | 624 hours |  | 10% | 31 |  | Normal | General
1.3.2.1 | Unit tests | 2019-01-21 00:00 | 10 days | 240 hours |  | 20% |  |  | Normal | General
1.3.2.2 | UI unit tests / individual screens | 2019-01-21 00:00 | 5 days | 120 hours |  | 10% |  |  | Normal | General
1.3.2.3 | Application tests | 2019-01-21 00:00 | 10 days | 240 hours |  | 0% |  |  | Normal | General
1.3.2.4 | Monkey tests | 2019-01-21 00:00 | 1 day | 24 hours |  | 0% |  |  | Normal | General
1.4 | Application Implementation | 2019-02-02 00:00 | 32 days | 2280 hours |  | 39% | 3 |  | Normal | General
1.4.1 | Phase #1 | 2019-02-02 00:00 | 7 days | 408 hours |  | 47% |  | 401 | Normal | General
1.4.1.1 | Authentication module | 2019-02-04 00:00 | 5 days | 120 hours |  | 100% |  | 45 | Normal | General
1.4.1.2 | Single sign on | 2019-02-04 00:00 | 3 days | 72 hours |  | 100% |  | 45 | Normal | General
1.4.1.3 | Implement role based access | 2019-02-04 00:00 | 4 days | 96 hours |  | 0% |  | 45 | Normal | General
1.4.1.4 | Basic test coverage | 2019-02-04 00:00 | 3 days | 72 hours |  | 0% |  | 45 | Normal | General
1.4.1.5 | Verify high test coverage | 2019-02-11 00:00 | 2 days | 48 hours |  | 0% | 41;42;43;44 |  | Normal | General
1.4.1.6 | Make backup | 2019-02-02 00:00 | 0 days | 0 hours |  | 0% |  |  | Normal | General
1.4.2 | Phase #2 | 2019-02-13 00:00 | 21 days | 1560 hours |  | 37% | 400 | 402 | Normal | General
1.4.2.1 | Authentication module | 2019-02-13 00:00 | 15 days | 360 hours |  | 70% |  |  | Normal | General
1.4.2.2 | Single sign on | 2019-02-13 00:00 | 5 days | 120 hours |  | 60% |  |  | Normal | General
1.4.2.3 | Implement role based access | 2019-02-13 00:00 | 21 days | 504 hours |  | 50% |  |  | Normal | General
1.4.2.4 | Basic test coverage | 2019-02-13 00:00 | 20 days | 480 hours |  | 0% |  |  | Normal | General
1.4.2.5 | Verify high test coverage | 2019-02-13 00:00 | 4 days | 96 hours |  | 0% |  |  | Normal | General
1.4.3 | Acceptance phase | 2019-03-14 00:00 | 4 days | 312 hours |  | 41% | 401 |  | Normal | General
1.4.3.1 | Company bug bash | 2019-03-14 00:00 | 3 days | 72 hours |  | 70% |  |  | Normal | General
1.4.3.2 | Test all web pages | 2019-03-14 00:00 | 2 days | 48 hours |  | 60% |  |  | Normal | General
1.4.3.3 | Verify no broken links | 2019-03-14 00:00 | 4 days | 96 hours |  | 50% |  |  | Normal | General
1.4.3.4 | Make test release | 2019-03-14 00:00 | 3 days | 72 hours |  | 0% |  | 4035 | Normal | General
1.4.3.5 | Send invitation email | 2019-03-19 00:00 | 0 days | 0 hours |  | 0% | 4034 |  | Normal | General
1.4.3.6 | Celebrate launch | 2019-03-14 00:00 | 1 day | 24 hours |  | 0% |  |  | Normal | General