## ProjectTaskList
Small Start 研發規劃
[10 empty] | {42} |  |  |  | Task List Templates
|  | Project Start | 2021-01-01 | [10 empty] | © 2017 Vertex42 LLC
PROJECT | TASK | PRIORITY | START | PLAN END | Days | ACTUAL END | % COMPLETE | Project Start | Days to Start | Complete | Incomplete | Slippage | Plan Days | programs
ADM |  | HIGH | 2021-01-01 | 2021-05-31 | 150 |  | 50% | 2021-01-01 | 0 | 75.5 | 75.5 | 0 | 151 | 53 | ADM (53)
WIP |  | LOW | 2021-01-01 | 2021-05-31 | 150 |  | 30% | 2021-01-01 | 0 | 45.3 | 105.7 | 0 | 151 | 57 | WIP (57)
EMS |  |  | 2021-06-01 | 2021-07-31 | 60 |  | 50% | 2021-01-01 | 151 | 30.5 | 30.5 | 0 | 61 | 40 | EMS (40)
MTS |  | LOW | 2021-08-01 | 2021-08-31 | 30 |  |  | 2021-01-01 | 212 | 0 | 31 | 0 | 31 | 27 | MTS (27)
QMS |  |  | 2021-04-01 | 2021-04-30 | 29 |  |  | 2021-01-01 | 90 | 0 | 30 | 0 | 30 | 16 | QMS (16)
WRP |  |  | 2021-04-01 | 2021-04-30 | 29 |  |  | 2021-01-01 | 90 | 0 | 30 | 0 | 30 | 18 | WRP (18)
SmartReport |  |  | 2021-05-01 | 2021-06-30 | 60 |  |  | 2021-01-01 | 120 | 0 | 61 | 0 | 61 | 13 | SmartReport (13)
LMS |  |  | 2021-08-01 | 2021-08-31 | 30 |  |  | 2021-01-01 | 212 | 0 | 31 | 0 | 31 | 8 | LMS (8)
EIS |  |  | 2021-09-01 | 2021-09-30 | 29 |  |  | 2021-01-01 | 243 | 0 | 30 | 0 | 30 | 13 | EIS (13)
SPC |  |  | 2021-09-01 | 2021-09-30 | 29 |  |  | 2021-01-01 | 243 | 0 | 30 | 0 | 30 | 11 | SPC (11)
Insert new rows above this one
[42]
Formulas:
PLAN END = [START]+[Days]

## Help
HELP |  | © 2017 Vertex42.com
https://www.vertex42.com/ExcelTemplates/task-list-template.html
About
This task list template shows how you can create a gantt chart as a stacked bar chart in Excel. The Project Start date is the first series in the chart, but it is shown as a hidden bar by changing the fill color to None. The Minimum bound for the x-axis should be set to the Project Start date (and that is a manual process - see below).
Try a better approach to creating Gantt charts in Excel
Get Gantt Chart Template Pro for Excel
Adjust the Minimum Bound for the X-axis
When you change the Project Start date, you will need to also update the Minimum bound for the X-axis in the gantt chart. Right-click on the x-axis labels in the chart and go to Format Axis.
Adding More Rows
When you insert new rows, you should insert a blank row, then copy formulas down in the columns with the gray background.
Conditional Formatting
The Priority column uses conditional formatting to highlight cells differently based on their text value. If you change the list of items in the Priority drop-down list, then you may need to edit the conditional formatting rule(s) as well.
To edit conditional formatting rules, go to Conditional Formatting > Manage Rules and select "This Worksheet" to see and edit all the rules.
Terms of Use
This spreadsheet, including all worksheets and associated content is a copyrighted work under the United States and other copyright laws.
Do not submit copies or modifications of this template to any website or online template gallery. Please review the following license agreement to learn how you may or may not use this template. Thank you.
https://www.vertex42.com/licensing/EULA_privateuse.html
Additional Help
The link at the top of this worksheet will take you to the web page on vertex42.com that talks about this template.